## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Member 1 | 2026-09-03 | Login fails with valid credentials | Sprint 1 | Member 2 | Functional | Fixed login validation logic | 2026-09-03 | Closed | Login working correctly
2 | Member 3 | 2026-09-03 | Invalid email accepted during registration | Sprint 1 | Member 1 | Validation | Added email validation | 2026-09-03 | Closed | Verified
3 | Member 4 | 2026-09-04 | Dashboard data not loading | Sprint 1 | Member 5 | Functional | Corrected database query | 2026-09-04 | Closed | Dashboard working
4 | Member 2 | 2026-09-04 | Profile image upload fails | Sprint 1 | Member 4 | Functional | Fixed file upload configuration | 2026-09-04 | Closed | Upload tested
5 | Member 5 | 2026-09-04 | Resume PDF upload not working | Sprint 2 | Member 6 | Functional | Updated PDF processing module | 2026-09-05 | Closed | PDF processing successful
6 | Member 6 | 2026-09-05 | AI interview questions not generated | Sprint 2 | Member 7 | AI/Backend | Fixed AI API integration | 2026-09-05 | Closed | Questions generated
7 | Member 7 | 2026-09-05 | Microphone not detected during interview | Sprint 2 | Member 8 | Browser/Functional | Updated microphone permission handling | 2026-09-06 | Open | Further testing required
8 | Member 8 | 2026-09-06 | Interview score calculated incorrectly | Sprint 2 | Member 6 | Algorithm | Reviewing evaluation logic | — | Open | Under investigation
9 | Member 9 | 2026-09-06 | Previous interview history not displayed | Sprint 3 | Member 2 | Database | Corrected history retrieval query | 2026-09-06 | Closed | Records displayed
10 | Member 10 | 2026-09-07 | Application error after deployment | Sprint 3 | Member 10 | Deployment | Checking server configuration | — | Open | Deployment issue

## Sheet2
Logical
User Interface
Maintainability
Standards
Others